## C15 Solder Defect
Supplier Corrective Action Request |  | Photos
AE SQE: | Emily Moey
Supplier: | PLEXUS
Supplier Contact: | yi-von.soo@plexus.com
SCAR # | NA
DMR # | 200524292
Problem Statement
On 13-Apr'20, AE feedback encountered capacitor C15 open solder. The solder joint looks like soldering tin insufficient and observed there is gap between capacitor and PCB. Model: 1309344 Affected S/N: 903425-2003-079C
Containment Actions
AE Containment Actions AE return the affected PCBA board to Plexus for further analysis. Plexus Containment Actions No inventory FG on hand for model 1309344.
Root-Cause Description
Plexus has taken few boards to measure on the Dow Corning 3-6265 height that dispensed between PCB pads for affected capacitors is fall between 5mils - 5.5mils. However the current stencil thickness is 5mils. This could potentially caused the capacitor termination to have less contact to the solder paste due to have slight high up after placing the caps onto the dow corning.
Solution
1. Fine tune AOI program to have more tighten spec and trigger operators to inspect on these caps. (PIC: YH Chang, Status: Closed, Date: 22-Jul-20) 2. Fabricate a new stencil of 8mils thickness to compensate the dow corning height in order to ensure sufficient solder amount printed onto PCB board. (PIC: Wooi-Kit, Status: Closed, Date: 11-Aug-20) 3. Monitor next build with the new 8mils stencil. (PIC: Wooi-Kit, Status: Open, Date: 14-Aug-20)